## Sheet1
2013-2014 Task Order Agreement # 119903
Task Order | Performance Period |  | Max (not-to-exceed) Approved Task Orders | Paid through Invoice #20 (September) and #21 (October) and SAAS | Paid through November Invoice # 22 (Due January 31) | Paid Through Invoice # 24 (December 2013) | January 2014 Invoice #25 | Feb Estimate | March Estimate | To Be Moved To Pending Agreement 2014 | Notes
TO #10 SAAS | 04/01/13 to 12/31/13 |  | 10800 | 6300 | 7200 | 8100 | 9000 | 9900 | 10800 | 0 | SAAS Services (Revision #1 attached)
TO#11 General Enhancements | 09/01/13 to 04/15/14 |  | 81914.28 | 16080.7 | 44976.64 | 44976.64 | 44976.64 | 44976.64 | 44976.64 | 36937.64 | (Need to change end date to 03/31/14)
TO#12 DCT/USGS Dashboards Needs Assessment | 09/01/13 to 04/15/14 |  | 21345.64 | 16169.9 | 21152.72 | 21152.72 | 21152.72 | 21152.72 | 21152.72 | 192.92 | (Need to change end date to 03/31/14)
TO #13 Project Dashboards | 09/01/13 to 04/15/14 |  | 47058.08 | 8903.92 | 8903.92 | 12688.24 | 12688.24 | 18796.96 | 18796.96 | 28261.12 | (Need to change end date to 03/31/14
TO #14 Delta Perspective Maps | 01/06/14 to 01/15/14 |  | 2123.8 |  |  |  | 2123.8 | 2123.8 | 2123.8 | 0
Total Spent of $163,241.80 | 240000 |  | 163241.8 | 47454.52 | 82233.28 | 86917.6 | 89941.4 | 96950.12 | 97850.12 | 65391.68
|  |  | Max (not-to-exceed) Approved Task Orders |  |  | Paid Through Invoice # 24 (December 2013) | January 2014 Invoice #25 |  |  | To Be Moved To Pending Agreement 2014
TO #15 Virtual Delta (Suisun Marsh) Tidal Cycle Variability | 01/06/14 to 02/28/14 |  | 11832.6 |  |  |  | 8646.9 | 11832.6 | 11832.6 | 0 | Not Approved Yet, Budget needs to be reconciled with available funds.. Task Order #15: Curt asked David to finish the animation? Need to extend date to 2/28/14
TO #16 Delta Conditions Team Data Management/OPS Decision Support Tool | 12/01/13 to 03/31/14 |  | 59667.54 |  |  | 7048.32 | 30927.8 | 59667.54 | 59667.54 | 0 | Not Approved Yet, Budget needs to be reconciled with available funds
TO #17 Water OPS Acoutic Telemetry Data (South Delta) | 12/01/13 to 03/31/14 |  | 71420.82 |  |  | 20860.24 | 41338.03 | 71420.82 | 71420.82 | 0 | Not Approved Yet, Budget needs to be reconciled with available funds
2013 Total | [5 empty] | 27908.56 | 80912.73 | 142920.96 | 142920.96 | 0
Invoices 2013 | Invoice #13 | Invoice 14-19 | 9/2013 Invoice #20 | 10/2013 Invoice #21 | 11/13 Invoices #22 | 12/13 Invoice #23 | 1/14 Invoice #24 | Feb 2014 Estimate | March estimate | Total | Total Agreement Year #3
|  | 5400 | 13073.9 | 28170.62 | 34778.76 | 32592.88 | 56027.97 | 52155.26 | 17500 | 239699.39 | 239699.39
300.61
Other Agreements
TO #03 BLACK & VEATCH AGREEMENT #120046 Delta Historic Ecology Model/Visualization | 01/06/14 to 03/10/14 |  | 70206.76 | [7 empty] | Not Approved Yet, Budget needs to be reconciled with available funds
Agreement Amount | 240000
Approved Task Orders | 163241.8 |  |  |  | 91900.78
Less Amount to be Reconciled from 2012 | 6826.5 |  |  |  | 95067.28
Amount Available New Tasks | 69931.7 |  |  |  | 3166.5
Add Back Deferred Work to 2014 Pending Agreement | 65391.68 | See H15
Total Available Critical Path Tasks | 135323.38
Total Remaining in Agreement and Deferred Work
`